# Work plan
## Deadlines
- 2015-03-02 Choose a project proposal and send the result via email to epsatisep@gmail.com
- 2015-03-11 Define the Tasks (what must be done), Task allocation (who does what) and Gantt chart (when) of the project and insert them on the wiki (planning)
- 2015-03-27 Specify the list of material (what, quantity, where to buy - local companies are mandatory) on the wiki
- 2015-04-05 Upload the Interim Report and Presentation to the wiki; the report should contain the Introduction, including the tasks, team members allocation and Gantt chart, State of the Art, Marketing Plan, Project Management, Eco-eficiency Measures for Sustainability, Ethical and Deontological Concerns, Proposed Solution and Bibliography chapters
- 2015-04-09 Interim Presentation, Discussion and Assessment
- 2015-06-12 Upload the Final Report, Presentation, Video, Paper, Poster and Manual
- 2015-06-18 Final Presentation, Individual Discussion and Assessment
- 2015-06-25:
  - Update the wiki with all correction suggestions
  - Hand in a CD with the corrected deliverables (source + PDF) together with all code produced to the EPS coordinator
  - Hand in one printed exemplar of the corrected report to the EPS coordinator
- 2015-06-26:
  - Hand in the prototype and user manual to the client
  - Receive the EPS@ISEP certificate
## Tasks
Task	Responsible
Project Selection	Entire Team
Gantt Chart	Imre and Thies
Team building Presentation	Entire Team
Leaflet	Thies
Material Research and Selection	Entire Team
State of the Art	Jonny and Marc
Marketing	Roberto and Thies
Energy and Sustainability	Imre
Ethics and Deontology	Gizem
Investigation	Entire Team
Planning	Entire Team
Development	Entire Team
Testing	Entire Team
Interim Report/Presentation	Entire Team
Final Report/Presentation	Entire Team
Poster	Marc and Imre
Paper	Gizem and Roberto
Manual	Entire Team
Video	Imre and Jonny
Logbook	Entire Team
Website	Jonny

## Gantt Chart

## Alternative Gantt Chart